Project Status Report

Ozone Interactive Study

As Of: October 27, 2025

Project Status Summary		Percent Complete:	8%

| Scope | Schedule | Cost | Risks | Quality |
| --- | --- | --- | --- | --- |

Schedule:  The project is on schedule.

Risks: There are currently no risks identified.

# Work Planned for Last Week

- Add a finishing slide for options on fixing our ozone problems

- Prepare to present the Design to the Sponsors

# Work Completed Last Week

- Add a finishing slide for options on fixing our ozone problems

- Prepare to present the Design to the Sponsors

# Work Planned For Next Week

- Complete the First Feature implementation project

- Present our initial plan to sponsors

- Complete Culture AI survey

- Complete a framework tutorial

# Open Issues

None

# Deliverables and Milestones

| Milestone | WBS | Planned | Forecasted | Actual | Status |
| --- | --- | --- | --- | --- | --- |
| Planning Stage | 1 | 10/22 |  |  | Completed |
| Execution Stage | 2 | 3/14 |  |  | In Progress |
| Deliverable | WBS | Planned | Forecasted | Actual | Status |
| Draft Design Slideshow | 1.1 | 10/15 |  |  | Completed |
| Draft Ending Slide For Solutions | 1.3 | 10/22 |  |  | Completed |
| Final Design Slideshow | 1.2 | 10/22 |  |  | Completed |

# Open Change Requests

No change requests as of now we are still in the planning stage of this project.

| Change Request Name | Change Request Number | Request Date | Current Status |
| --- | --- | --- | --- |

# Key Performance Indicators (KPI's)

Schedule - Project is On Schedule

Schedule Variance (SV):	0 days